## Traceability Matrix
REQUIREMENTS TRACEABILITY MATRIX
PROJECT ID: | Facebook_001
PROJECT TITLE: | Facebook
Requirement | Test Suit ID | Test Case ID | Related Bug ID | PRIORITY
RF1 | 1 | FaceGUI01
FaceGUI02
FaceGUI03
FaceGUI04
FaceGUI05
FaceGUI06
FaceGUI07
|  | FaceGUI08 | Facebug#1 | medum
| 2 | Facepossetiv36 | Facebug#2 | high
| 3 | Facenegativ46
Facenegativ47
FR2 | 4 | FaceStoryGUI61
FaceStoryGUI62
| 5 | FaceStorypost83
FaceStorypost84
| 6 | FaceStorynegat100
FaceStorynegat101
FR3 | 7
|  | FaceMessgGUI107 | Facebug#3 | high
8
9

## Requiermentanalist
Ambiguous and Questions
Check user can create new post from hom page or profile page
Check user can Identifies who can see the post
Check user can add multi photo
Check user can back before the post is publishing
Check user can share text , photo ,video , gif ,music , back ground color , use camera to tack a photo , layouts , check in (location) ,live video ,feeling /activity
User can use Filters post filters
Check user can veiw his post
Check user can Manage posts
Check user can use photos and Avatars butons
Check user can use Life events and music butons
Check user can add story from home page
Check user can add story from profile page
Check if your story visible for 24 hours on facebook and messenger
Check user can add Text in a story , select simple line type and back ground colure.
Chek user can add music from suggested music in Facebook
Check user can add video by camera
check user can add photo by camera
Check user can select multible photo or video or mix from gallery
Chek user can add a photo gallery
Check user can edit story settings
Check user can edit story comments
check user can Search about any friend to connecting with this friend by video call
check user can Send the same one message or more to one or more friend
check user can oppen chat with friend
check user can display his friend profile from chat
check user can edit settingg from chat
check user can share his links or files with his friends by chat
check user can display his friend links or files it to user in the chat
check user can Search about any person in Facebook to connect with thim
Make a voice call with your friend from chat
Make a video call with your friend from chat

## GENERAL
TC ID | TC Name | Precondition | 0 | testeData | ExpectedResult | ActualResult | priority | status | requierment traciabilty | bug traciabilty | test type | medeule name
FaceGUI01 | verefy user able to create new text poste from home | Facebook App is instaling and oppening | open Facebook app ,login your account click on what's on your mined? write your text , click post |  | new post is created | poste is created | high | pass |  |  | GUI | adding post
FaceGUI02 | verefy user able to create new photo post from home by photo icon |  | open Facebook app ,login your account home page, click on photo icon select your photos from gallary,,Next ,POST |  | new photo post is created | new photo post is created | high | Pass |  |  | GUI | adding post
FaceGUI03 | verefy user able to specifing who can see his post?friends |  | open Facebook app ,login your account home page, lick on what's on your mined? click on post audience, select frends |  | your audience is your friends | your audience is your friends | high | pass |  |  | GUI | adding post
FaceGUI04 | verefy user able to add feeling to the post |  | open Facebook app ,login your account home page,click on what's on your mined? click on face icon ,select your feeling click done ,POST |  | add fealing | add fealing | low | pass |  |  | GUI | adding post
FaceGUI05 | verify user able to tag people in the post |  | open Facebook app ,login your account home page, click on what's on your mined? click on tag people , post |  | tage people in the post | tage people in the post | medum | pass |  |  | GUI | adding post
FaceGUI06 | verefy user able to add effect to the post photo |  | open Facebook app ,login your account home page , click on what's on your mined? click on photo icon , select your photos from gallary Next , add effect to the photo ,POST |  | effect is adding | effect is adding | medum | pass |  |  | GUI | adding post
FaceGUI07 | verefy user able to add filter to the post photo |  | open Facebook app ,login your accoun home paget , click on what's on your mined? click on photo icon , select your photos from gallary Next , add filter to the photo ,Post |  | filter is adding | filter is adding | medum | pass |  |  | GUI | adding post
FaceGUI08 | verefy user able to add effect to the post video |  | open Facebook app ,login your account home page , click on what's on your mined? click on photo icon , select your video from gallary Next , add effect to the photo ,Post |  | effect is adding | the app hanging | medum | fail |  |  | GUI | adding post
FaceGUI09 | verefy user able to add video from gallary with photo from camera and text to the post |  | open Facebook app ,login your account home page , click on what's on your mined? write text , click on photo icon select your video from gallary, Next add photo from camera to the photo ,Post |  | photo with video and text is added | photo with video and text is added | medum | pass |  |  | GUI | adding post
FaceGUI10 | verefy user able to add video from the camera |  | open Facebook app ,login your account home page , click on what's on your mined? select camera,select video,recored video,done , post |  | video is posted | video is posted | high | pass |  |  | GUI | adding post
FaceGUI11 | verefy user able to add photo from the camera |  | open Facebook app ,login your account home page , click on what's on your mined? select camera , tack photo, done , post |  | photo is posted | photo is posted | high | pass |  |  | GUI | adding post
FaceGUI12 | verefy user able to add gif |  | open Facebook app ,login your account home page , click on what's on your mined? click on gif icon ,select your gif , don ,post |  | gif is posted | gif is posted | medum | pass |  |  | GUI | adding post
FaceGUI13 | verefy user able to add music |  | open Facebook app ,login your account home page , click on what's on your mined? click on music icon ,select your music , don ,post |  | music is posted | music is posted | medum | pass |  |  | GUI | adding post
FaceGUI14 | verefy user able to add locasion |  | open Facebook app ,login your account , home page click on what's on your mined? click oncheck in icon ,allow app oppen location select location ,done , post |  | is posted | [5 empty] | GUI | adding post
FaceGUI15 | verefy user able to create new poste text with photo from gallary |  | open Facebook app ,login your account home page click on what's on your mined? write your text , click on photo icon select your photos,Next ,POST |  | post is added | post is added | high | pass |  |  | GUI | adding post
FaceGUI16 | verefy user able to create new photo post from profile page by photo icon beside what's on your mined? |  | open Facebook app ,login your account profile page, click on photo icon select your photos from gallary,Next ,POST |  | new photo post is created | new photo post is created | high | Pass |  |  | GUI | adding post
FaceGUI17 | verefy user able to create new text poste from profile page | Facebook App is instaling and oppening | open Facebook app ,login your account profile page click on what's on your mined? write your text , click post |  | new post is created | poste is created | high | pass |  |  | GUI | adding post
FaceGUI18 | verefy user able to create new photo post from profile page by photo icon in what's on your mined? |  | open Facebook app ,login your account profile page,what's on your mined?, click on photo icon select your photos from gallary,,Next ,POST |  | new photo post is created | new photo post is created | high | Pass |  |  | GUI | adding post
FaceGUI19 | verefy user able to specifing who can see his post? friends from profile page |  | open Facebook app ,login your account profile page, lick on what's on your mined? click on post audience, select friends |  | your audience is your friends | your audience is your friends | high | pass |  |  | GUI | adding post
FaceGUI20 | verefy user able to add feeling to the post from profile page |  | open Facebook app ,login your account profile page,click on what's on your mined? click on face icon ,select your feeling click done ,POST |  | add fealing | add fealing | low | pass |  |  | GUI | adding post
FaceGUI21 | verify user able to tag people in the post from profile page |  | open Facebook app ,login your account profile page, click on what's on your mined? click on tag people , post |  | tage people in the post | tage people in the post | medum | pass |  |  | GUI | adding post
FaceGUI22 | verefy user able to add effect to the post photo from profile page |  | open Facebook app ,login your account profile page , click on what's on your mined? click on photo icon , select your photos from gallary Next , add effect to the photo ,POST |  | effect is adding | effect is adding | medum | pass |  |  | GUI | adding post
FaceGUI23 | verefy user able to add filter to the post photo from profile page |  | open Facebook app ,login your accoun profile page , click on what's on your mined? click on photo icon , select your photos from gallary Next , add filter to the photo ,Post |  | filter is adding | filter is adding | medum | pass |  |  | GUI | adding post
FaceGUI24 | verefy user able to add effect to the post video from profile page |  | open Facebook app ,login your account profile page , click on what's on your mined? click on photo icon , select your video from gallary Next , add effect to the photo ,Post |  | effect is adding | the app hanging | medum | fail |  |  | GUI | adding post
FaceGUI25 | verefy user able to add video from gallary with photo from camera and text to the post from profile page |  | open Facebook app ,login your account profile page , click on what's on your mined? write text , click on photo icon select your video from gallary, Next add photo from camera to the photo ,Post |  | photo with video and text is added | photo with video and text is added | medum | pass |  |  | GUI | adding post
FaceGUI26 | verefy user able to add video from the camera from profile page |  | open Facebook app ,login your account profile page , click on what's on your mined? select camera,select video,recored video,done , post |  | video is posted | video is posted | high | pass |  |  | GUI | adding post
FaceGUI27 | verefy user able to add photo from the camera from profile page |  | open Facebook app ,login your account profile page , click on what's on your mined? select camera , tack photo, done , post |  | photo is posted | photo is posted | high | pass |  |  | GUI | adding post
FaceGUI28 | verefy user able to add gif from profile page |  | open Facebook app ,login your account profile page , click on what's on your mined? click on gif icon ,select your gif , don ,post |  | gif is posted | gif is posted | medum | pass |  |  | GUI | adding post
FaceGUI29 | verefy user able to add music from profile page |  | open Facebook app ,login your account profile page , click on what's on your mined? click on music icon ,select your music , don ,post |  | music is posted | music is posted | medum | pass |  |  | GUI | adding post
FaceGUI30 | verefy user able to add locasion from profile page |  | open Facebook app ,login your account , profile page click on what's on your mined? click oncheck in icon ,allow app oppen location select location ,done , post |  | is posted | [5 empty] | GUI | adding post
FaceGUI31 | verefy user able to create new post text with photo from gallary from profile page |  | open Facebook app ,login your account from profile page click on what's on your mined? write your text , click on photo icon select your photos,Next ,POST |  | post is added | post is added | high | pass |  |  | GUI | adding post
FaceGUI32 | verefy user able to create new post live from home and profile page |  | open Facebook app ,login your account from home page or profile page click on what's on your mined? click on live icon start live,finish ,Post to profile |  | live is added | live is added | medum | pass |  |  | GUI | adding post
FaceGUI33 | verify filters worke sucsisfuly |  | open Facebook app ,login your account from profile page click on filters select your filter,Done |  | only veiw related postes | only veiw related postes | medum | pass |  |  | GUI | adding post
FaceGUI34 | verify live icon under what's on your mined? worke sucsisfuly |  | open Facebook app ,login your account from profile page click on live icon start live,finish ,Post to profil |  | live is added | live is added | medum | pass |  |  | GUI | adding post
Facepossetiv35 | verefy user able to delet post |  | open Facebook app ,login your account from profile page click on manage posts select post , click on junk icon Delet posts,DELETPOSTS in message |  | post is deleting | post is deleting | high | pass |  |  | Positive | adding post
Facepossetiv36 | verefy user able to Remove tags from posts |  | open Facebook app ,login your account from profile page click on manage posts select tags post , click on tags icon Remove tags |  | tage is Remove | tage tag icon unactive | high | fail |  |  | Positive | adding post
Facepossetiv37 | verefy user able to finish his post later |  | open Facebook app ,login your account profile page or home page click on what's on your mined? write your text , click bake select save as draft | [7 empty] | Positive | adding post
Facepossetiv38 | verefy user able to Discard post his post later |  | open Facebook app ,login your account profile page or home page click on what's on your mined? write your text , click bake Discard post | [7 empty] | Positive | adding post
Facepossetiv39 | verefy user able to specifing his post audience |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on audience butne ,select your audience | [7 empty] | Positive | adding post
Facepossetiv40 | verefy user able to creat new album |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on album ,creat new albom | [7 empty] | Positive | adding post
Facepossetiv41 | verefy user able to add posts to album |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on album,select your album | [7 empty] | Positive | adding post
Facepossetiv42 | verefy user able to share his post photo to Instagram |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on Instagram icon turn on Instagram | [7 empty] | Positive | adding post
Facenegativ43 | verefy user able to share his text post to Instagram |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Write your post Click on Instagram icon turn on Instagram | [7 empty] | Negativ | adding post
Facenegativ44 | verefy user able to share his audues post to Instagram |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on music Select your audue Click on Instagram icon turn on Instagram | [7 empty] | Negativ | adding post
Facenegativ45 | verefy user able to share his audues post to Instagram |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on chick in Select your location Click on Instagram icon turn on Instagram | [7 empty] | Negativ | adding post
Facenegativ46 | verefy user able to share his fealing only in post to Instagram |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on feeling Select your fealing Click on Instagram icon turn on Instagram | [7 empty] | Negativ | adding post
Facenegativ47 | verefy user able to share background color post to Instagram |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on background color Select your background color Click on Instagram icon turn on Instagram | [7 empty] | Negativ | adding post
Facenegativ48 | verefy user able to add photo with text extention | [9 empty] | Negativ | adding post
Facenegativ49 | verefy user able to add video with text extention | [9 empty] | Negativ | adding post
Facenegativ50 | verefy user able to add video violent content | [9 empty] | Negativ | adding post
FaceStoryGUI51 | verefy user able to add text story |  | open Facebook app ,login your account profile page click add to story or home page creat story select text , write your text Done ,share |  | New story text is adding | new story text is adding | high | pass |  |  | GUI | adding story
FaceStoryGUI52 | verefy user able to add music story |  | open Facebook app ,login your account profile page click add to story or home page creat story click music , select music Done ,share |  | New music story is adding | New music story is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI53 | verefy user able to add green screen photo story |  | open Facebook app ,login your account profile page click add to story click green screen , select scenes tacke a photo ,Done ,share |  | New story with green screen photo is adding | New story with green screen photo is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI54 | verefy user able to add green screen photo with music story |  | open Facebook app ,login your account profile page click add to story click green screen , select scenes tacke a photo , select your music ,Done ,share |  | New story with green screen photo and music is adding | New story with green screen photo and music is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI55 | verefy user able to add multi story |  | open Facebook app ,login your account profile page click add to story select text , write your text Done ,share click add to story click music , select music Done ,share |  | New story with text and music is adding | New story with text and music is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI56 | verefy user able to add BOOMERANG photo story |  | open Facebook app ,login your account profile page click add to story click BOOMERANG tacke a photo ,Done ,share |  | New story with Boomerang photo is adding | New story with Boomerang photo is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI57 | verefy user able to add Boomerang photo with music story |  | open Facebook app ,login your account profile page click add to story click BOOMERANG tacke a photo , select your music ,Done ,share |  | New story with Boomerang photo and music is adding | New story with Boomerang photo and music is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI58 | verefy user able to add selfie photo story |  | open Facebook app ,login your account profile page click add to story click selfie tacke a photo ,share |  | New story with selfie photo is adding | New story with selfie photo is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI59 | verefy user able to add selfie photo with music story |  | open Facebook app ,login your account profile page click add to story click selfie tacke a photo , select your music ,share |  | New story with selfie photo and music is adding | New story with selfie photo and music is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI60 | verefy user able to add effect to music story |  | open Facebook app ,login your account profile page click add to story click music , select music add effect ,Done ,share |  | New music story with effect is adding | New music story with effect is adding | low | pass |  |  | GUI | adding story
FaceStoryGUI61 | verefy user able to add effect to green screen photo story |  | open Facebook app ,login your account profile page click add to story click green screen , select scenes tacke a photo , add effect ,Done ,share |  | New story with green screen photo and effect is adding | New story with green screen photo and effect is adding | low | pass |  |  | GUI | adding story
FaceStoryGUI62 | verefy user able to add effect to Boomerang photo story |  | open Facebook app ,login your account profile page click add to story click BOOMERANG tacke a photo , select effect ,Done ,share |  | New story with Boomerang photo and effect is adding | New story with Boomerang photo and effect is adding | low | pass |  |  | GUI | adding story
FaceStoryGUI63 | verefy user able to add effect to selfie photo story |  | open Facebook app ,login your account profile page click add to story click selfie , select effect tacke a photo ,share |  | New story with selfie photo and effect is adding | New story with selfie photo and effect is adding | low | pass |  |  | GUI | adding story
FaceStoryGUI64 | verefy user able to add green screen video with music story |  | open Facebook app ,login your account profile page click add to story click green screen , select scenes hold to record a video , select your music Done ,share |  | New story with green screen video is adding | New story with green screen video is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI65 | verefy user able to add Boomerang video with music story |  | open Facebook app ,login your account profile page click add to story select Boomerang hold on BOOMERANG record a video select your music ,Done ,share |  | New story with Boomerang video is adding | New story with Boomerang video is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI66 | verefy user able to add selfie video with music story |  | open Facebook app ,login your account profile page click add to story click selfie record a video , select sound , add music select your music ,share |  | New story with silfie video is adding | New story with selfie video is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI67 | verefy user able to add effect to green screen video story |  | open Facebook app ,login your account profile page click add to story click green screen , select scenes hold to record a video , click on effects select effect ,Done ,share |  | New story with green screen video and effect is adding | New story with green screen video and effect is adding | low | pass |  |  | GUI | adding story
FaceStoryGUI68 | verefy user able to add effect to Boomerang video story |  | open Facebook app ,login your account profile page click add to story click BOOMERANG hold to record a video , click on effects select effect ,Done ,share |  | New story with Boomerang video and effect is adding | New story with Boomerang video and effect is adding | low | pass |  |  | GUI | adding story
FaceStoryGUI69 | verefy user able to add effect to selfie video story |  | open Facebook app ,login your account profile page click add to story click selfie ,hold to record a video click on effects select effect,share |  | New story with silfie video and effect is adding | New story with silfie video and effect is adding | low | pass |  |  | GUI | adding story
FaceStoryGUI70 | verefy user able to add a photo from camera to story |  | open Facebook app ,login your account profile page click add to story click camera icon ,tacke a photo , share |  | New story with camera photo is adding | New story with camera photo is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI71 | verefy user able to add a photo from camera with music and effect to story |  | open Facebook app ,login your account profile page click add to story click camera icon ,select your effect tacke a photo select your music , share |  | New story with camera photo and effects is adding | New story with camera photo and effects is adding | low | pass |  |  | GUI | adding story
FaceStoryGUI72 | verefy user able to add a video from camera to story |  | open Facebook app ,login your account profile page click add to story click camera icon ,select video record the video, share |  | New story with camera video is adding | New story with camera video is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI73 | verefy user able to add a video from camera with music and effect to story |  | open Facebook app ,login your account profile page click add to story click camera icon ,select video record the video , click on effects select your effect select your music , share |  | New story with camera video , music and effects is adding | New story with camera video ,music and effects is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI74 | verefy user able to add a photo from gallery to story |  | open Facebook app ,login your account profile page click add to story select photo from gallery , share |  | New story with gallery photo is adding | New story with gallery photo is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI75 | verefy user able to add effects to the photo from gallery to story |  | open Facebook app ,login your account profile page click add to story select photo from gallery , click on effects select your effect , share |  | New story with gallery photo and effects is adding | New story with gallery photo and effects is adding | medum | pass |  |  | GUI | adding story
FaceStoryGUI76 | verefy user able to add a photo from gallery with music to story |  | open Facebook app ,login your account profile page click add to story select photo from gallery , select music , share |  | New story with gallery photo and music is adding | New story with gallery photo and music is adding | medum | pass |  |  | GUI | adding story
FaceStorypost77 | verefy user able to add a video from gallery to story |  | open Facebook app ,login your account profile page click add to story select video from gallery , share |  | New story with gallery video is adding | New story with gallery video is adding | medum | pass |  |  | Positive | adding story
FaceStorypost78 | verefy user able to add effects to the video from gallery to story |  | open Facebook app ,login your account profile page click add to story select video from gallery , click on effects select your effect , share |  | New story with gallery video and effects is adding | New story with gallery video and effects is adding | low | pass |  |  | Positive | adding story
FaceStorypost79 | verefy user able to add a video from gallery with music to story |  | open Facebook app ,login your account profile page click add to story select video from gallery , select music , share |  | New story with gallery video and music is added | New story with gallery video and music is added | medum | pass |  |  | Positive | adding story
FaceStorypost80 | verefy user able to always share green screen photo with music story to instagram |  | open Facebook app ,login your account profile page click add to story click green screen , select scenes click to tacke photo , select your music click on privacy ,Always share to instagram turn on ,share |  | New story with green screen photo and music is shared to facebook story and instagram | New story with green screen photo and music is shared to facebook story and instagram | medum | pass |  |  | Positive | adding story
FaceStorypost81 | verefy user able to always share Boomerang photo with music story to instagram |  | open Facebook app ,login your account profile page click add to story select Boomerang,click Boomerang , click to tacke photo , select your music click on privacy ,Always share to instagram turn on ,share |  | New story Boomerang photo with music is shared to facebook story and instagram | New story Boomerang photo with music is shared to facebook story and instagram | medum | pass |  |  | Positive | adding story
FaceStorypost82 | verefy user able to always share selfie photo with music story to instagram |  | open Facebook app ,login your account profile page click add to story click selfie click to tacke photo , select your music click on privacy ,Always share to instagram turn on ,share |  | New story selfie photo with music is shared to facebook story and instagram | New story selfie photo video with music is shared to facebook story and instagram | medum | pass |  |  | Positive | adding story
FaceStorypost83 | verefy user able to always share a photo from gallery with music story to instagram |  | open Facebook app ,login your account profile page click add to story select photo from gallery , select music click on privacy ,Always share to instagram turn on , share |  | New story gallery photo with music is shared to facebook story and instagram | New story gallery photo with music is shared to facebook story and instagram | medum | pass |  |  | Positive | adding story
FaceStorypost84 | verefy user able to always share a photo from camera with music story to instagram |  | open Facebook app ,login your account profile page click add to story click camera icon ,tacke a photo, select music click on privacy ,Always share to instagram turn on , share |  | New story camera photo with music is shared to facebook story and instagram | New story camera photo with music is shared to facebook story and instagram | medum | pass |  |  | Positive | adding story
FaceStorypost85 | verefy user able to always share a video from gallery with music story to instagram |  | open Facebook app ,login your account profile page click add to story select video from gallery , select music click on privacy ,Always share to instagram turn on , share |  | New story gallery video with music is shared to facebook story and instagram | New story gallery video with music is shared to facebook story and instagram | medum | pass |  |  | Positive | adding story
FaceStorypost86 | verefy user able to always share a video from camera with music story to instagram |  | open Facebook app ,login your account profile page click add to story click camera icon ,select video record the video, select music click on privacy ,Always share to instagram turn on , share |  | New story camera video with music is shared to facebook story and instagram | New story camera video with music is shared to facebook story and instagram | medum | pass |  |  | Positive | adding story
FaceStorypost87 | verefy user able to always share green screen video with music story to instagram |  | open Facebook app ,login your account profile page click add to story click green screen , select scenes hold to record a video , select your music click on privacy ,Always share to instagram turn on ,share |  | New story green screen video with music is shared to facebook story and instagram | New story green screen video with music is shared to facebook story and instagram | medum | pass |  |  | Positive | adding story
FaceStorypost88 | verefy user able to always share Boomerang photo with music story to instagram |  | open Facebook app ,login your account profile page click add to story select Boomerang,click Boomerang , hold to record a video , select your music click on privacy ,Always share to instagram turn on ,share |  | New story Boomerang video with music is shared to facebook story and instagram | New story Boomerang video with music is shared to facebook story and instagram | medum | pass |  |  | Positive | adding story
FaceStorypost89 | verefy user able to always share selfie photo with music story to instagram |  | open Facebook app ,login your account profile page click add to story click selfie hold to record a video , select your music click on privacy ,Always share to instagram turn on ,share |  | New story selfie video with music is shared to facebook story and instagram | New story selfie video with music is shared to facebook story and instagram | medum | pass |  |  | Positive | adding story
FaceStorypost90 | verefy user able to select multiple photo from gallery |  | open Facebook app ,login your account profile page or home creat story click add to story click select multiple ,select your photos click Next,click share. | [7 empty] | Positive | adding story
FaceStorypost91 | verefy user able to select multiple photo from gallery and add music to every photo |  | open Facebook app ,login your account profile page or home creat story click add to story click select multiple ,select your photos edit every photo ,select music to every photo click Next,click share. | [7 empty] | Positive | adding story
FaceStorypost92 | verefy user able to select multiple video from gallery |  | open Facebook app ,login your account profile page or home creat story click add to story click select multiple ,select your videos click Next,click share. | [7 empty] | Positive | adding story
FaceStorypost93 | verefy user able to select multiple videos from gallery and add music to every video |  | open Facebook app ,login your account profile page or home creat story click add to story click select multiple ,select your videos edit every video ,select music to every video click Next,click share. | [7 empty] | Positive | adding story
FaceStorypost94 | verefy user able to select multiple photo from gallery and add effects to them |  | open Facebook app ,login your account profile page or home creat story click add to story click select multiple ,select your photos edit every photo , click effects select effect to every photo click Done , click share. | [7 empty] | Positive | adding story
FaceStorypost95 | verefy user able to select multiple video from gallery and add effects to them |  | open Facebook app ,login your account profile page or home creat story click add to story click select multiple ,select your videos edit every video , click effects select effect to every video click Done , click share. | [7 empty] | Positive | adding story
FaceStorypost96 | verefy user able to select multiple videos and photos from gallery and add stickers to them |  | open Facebook app ,login your account profile page or home creat story click add to story click select multiple ,select your videos and photos ,edit every video and photo click stickers ,select stickers to every video and photo click Done , click share. | [7 empty] | Positive | adding story
FaceStorynegat97 | verefy user able to always share music story to instagram |  | open Facebook app ,login your account profile page click add to story click music , select your music click on privacy ,Always share to instagram turn on ,share | [7 empty] | Positive | adding story
FaceStorynegat98 | verefy user able to always share text story to instagram |  | open Facebook app ,login your account profile page click add to story click text , write your text click on privacy ,Always share to instagram turn on ,share | [7 empty] | Negativ | adding story
FaceStorynegat99 | verefy user able to edit his story privacy public when he locked his profile |  | open Facebook app ,login your account profile page click add to story , add your photo or video or any type of storeis by any way click on privacy,select public | [7 empty] | Negativ | adding story
FaceStorynegat100 | verify user story is visible after 24 hour on face book and messenger |  | open Facebook app ,login your account veiw your story or click on messenger icon to go to messenger , veiw your story after 25 hour | [7 empty] | Negativ | adding story
FaceStorynegat101 | verify user able to custom friend and hide the same story from the same friend |  | open Facebook app ,login your account profile page click add to story , add your photo or video or any type of storeis by any way click on privacy,select custom select singl friend ,click hid story from the same singl friend | [7 empty] | Negativ | adding story
FaceStorynegat102 | verify friend able to see your story you are hide this story from this friend |  | open Facebook app ,login your anather account oppen stories are you see the story | [7 empty] | Negativ | adding story
FaceStorynegat103 | verify friend able to comment in your story you are turn comments off for this story |  | open Facebook app ,login your anather account oppen stories try to comment in the story | [7 empty] | Negativ | adding story
FaceMessgGUI104 | verify user able to oppen chating with any friend |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him |  | chat is oppened | chat is oppened | high | pass |  |  | GUI | messeging
FaceMessgGUI105 | verify user able to send text messege in chat to his friend friend |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him write your text messege , click send |  | messege is sent | messege is sent | high | pass |  |  | GUI | messeging
FaceMessgGUI106 | verify user able to send a messege by pen icon to singel friend |  | open Facebook app ,login your account click on messenger icon click on pen icon select your single friend write your messege , click send |  | messege is sent | messege is sent | high | pass |  |  | GUI | messeging
FaceMessgGUI107 | verify user able to by send messege by pen icon to multi friend |  | open Facebook app ,login your account click on messenger icon click on pen icon select your multi friend write your messege , click send |  | messege is sent to praivte chat | messege is sent with creat grope | high | fail |  |  | GUI | messeging
FaceMessgGUI108 | verify user able to see his new notification from chats icon when it will be blue |  | open Facebook app ,login your account click on messenger icon click on chats icon |  | user notfication is oppend | user notfication is oppend | high | pass |  |  | GUI | messeging
FaceMessgGUI109 | verify user able to search about any one on facebook to chat with this person |  | open Facebook app ,login your account click on messenger icon in search tabe write name click search , select name start chating |  | veiw related result | veiw related result | medum | pass |  |  | GUI | messeging
FaceMessgGUI110 | verify user able to search about any friend in facebook to chat with this friend |  | open Facebook app ,login your account click on messenger icon in search tabe write your friend name click search , select your friend start chating |  | veiw related result | veiw related result | high | pass |  |  | GUI | messeging
FaceMessgGUI111 | verify user able to connect by video call with any single friend in facebook by start call icon |  | open Facebook app ,login your account click on messenger icon click start call icon select friend , click start call button |  | call is started | call is started | high | pass |  |  | GUI | messeging
FaceMessgGUI112 | verify user able to connect by video call with multibl friend in facebook by start call icon |  | open Facebook app ,login your account click on messenger icon click start call icon select 2 friends or more , click start call button |  | call is started | call is started | high | pass |  |  | GUI | messeging
FaceMessgGUI113 | verify user able to send a photo from gallery in messege in chat to friend |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo , click send |  | photo Message delivered | photo Message delivered | high | pass |  |  | GUI | messeging
FaceMessgGUI114 | verify user able to send a photo from camera in messege in chat to friend |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on camera icon , tacke photo, click send |  | takes a picture with the camera and it sent | takes a picture with the camera and it sent | high | pass |  |  | GUI | messeging
FaceMessgGUI115 | verify user able to send a voice note in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him holde on microphon icon ,say what you want , Lift your finger |  | voice note is sent | voice note is sent | high | pass |  |  | GUI | messeging
FaceMessgGUI116 | verify user able to send a like expretion in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click in like icon |  | like simpole is sent | like simpole is sent | low | pass |  |  | GUI | messeging
FaceMessgGUI117 | verify user able to send location in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click in four duts ,click on location icon define your locatoin , send location |  | right location is sent | right location is sent | high | pass |  |  | GUI | messeging
FaceMessgGUI118 | verify user able to send a voice note from chat to anther chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on share icon ,beside the voice note , click send beside any friend you need |  | voice note is sent to your selected friends | voice note is sent to your selected friends | medum | pass |  |  | GUI | messeging
FaceMessgpostiv119 | verify user able to send an emojy in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him in writing tabe click on emojy select your emojy , send |  | emojy is sent | emojy is sent | medum | pass |  |  | positive | messeging
FaceMessgpostiv120 | verify user able to send a gif in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him in writing tabe click on emojy ,click gif icon select your gif |  | gif is sent | gif is sent | low | pass |  |  | positive | messeging
FaceMessgpostiv121 | verify user able to send sounds in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him in writing tabe click on emojy ,click sound icon select your sound , send |  | sound is sent | sound is sent | low | pass |  |  | positive | messeging
FaceMessgpostiv122 | verify user able to send stickers in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him in writing tabe click on emojy ,click stickers icon select and click on your sticker |  | sticker is sent | sticker is sent | low | pass |  |  | positive | messeging
FaceMessgpostiv123 | verify user able to send star stickers in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him in writing tabe click on emojy ,click star icon select and click on your sticker |  | sticker is sent | sticker is sent | low | pass |  |  | positive | messeging
FaceMessgpostiv124 | verify user able to send video from gallery in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your video , ,click send |  | video is sent | video is sent | high | pass |  |  | positive | messeging
FaceMessgpostiv125 | verify user able to send video from gallery with sticker in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your video, click edit select sticker , done , click send |  | video is sent with sticker | video is sent with sticker | medum | pass |  |  | positive | messeging
FaceMessgpostiv126 | verify user able to send multi video from gallery in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your videos , ,click send |  | videos is sent | videos is sent | medum | pass |  |  | positive | messeging
FaceMessgpostiv127 | verify user able to send video from gallery with cut it in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your video, click edit click cut icon , cut video , click send |  | cuting video is sent | cuting video is sent | high | pass |  |  | positive | messeging
FaceMessgpostiv128 | verify user able to send video from gallery with text in video in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your video, click edit click text icon , write text in video done , click send |  | video with text is sent | video with text is sent | medum | pass |  |  | positive | messeging
FaceMessgpostiv129 | verify user able to send video from gallery with a drawing in video in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your video, click edit click brush icon , draw in video done , click send |  | video with adrawing is sent | video with adrawing is sent | medum | pass |  |  | positive | messeging
FaceMessgpostiv130 | verify user able to send photo from gallery with sticker in in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo, click edit select sticker , done , click send |  | photo is sent with sticker | photo is sent with sticker | low | pass |  |  | positive | messeging
FaceMessgpostiv131 | verify user able to send multi photo from gallery in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photos , ,click send |  | photos is sent | photos is sent | medum | pass |  |  | positive | messeging
FaceMessgpostiv132 | verify user able to send photo from gallery with cropt it in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo , click edit click cropt icon , cropt photo done , click send |  | cropted photo is sent | cropted photo is sent | high | pass |  |  | positive | messeging
FaceMessgpostiv133 | verify user able to send photo from gallery with text in photo in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo click edit click text icon ,select text aligne or text backgraund write text in photo done , click send |  | photo with text is sent | photo with text is sent | medum | pass |  |  | positive | messeging
FaceMessgpostiv134 | verify user able to send photo from gallery with a drawing in photo in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo click edit click brush icon , draw in photo done , click send |  | photo with adrawing is sent | photo with adrawing is sent | medum | pass |  |  | positive | messeging
FaceMessgpostiv135 | verify user able to send photo from gallery with an effect photo in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo click edit click effects icon , select your effect done , click send |  | photo with effect is sent | photo with effect is sent | low | pass |  |  | positive | messeging
FaceMessgpostiv136 | verify user able to send photo from gallery with a filter photo in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo click edit click filters icon , select your filter done , click send | [7 empty] | positive | messeging
FaceMessgpostiv137 | verify user able to send photo from gallery with a coloradjustment photo in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo click edit click coloradjustment icon , select your coloradjustment done , click send | [7 empty] | positive | messeging
FaceMessgpostiv138 | verify user able to send photo from camera by camera icon beside the sent photos in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on cameraicon beside the sent photos in chat , tacke a photo click send | [7 empty] | positive | messeging
FaceMessgpostiv139 | verify user able to send photo from camera by camera icon beside the sent photos in chat with sticker |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on cameraicon beside the sent photos in chat , tacke a photo click edit , select sticker done , click send | [7 empty] | positive | messeging
FaceMessgpostiv140 | verify user able to send photo from camera by camera icon beside the sent photos in chat with effect |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on camera icon beside the sent photos in chat , tacke a photo click edit , select effect done , click send | [7 empty] | positive | messeging
FaceMessgpostiv141 | verify user able to send text photo from camera in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on camera icon , select text photo write a text , click send | [7 empty] | positive | messeging
FaceMessgpostiv142 | verify user able to send video from camera in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on camera icon , record a video click send | [7 empty] | positive | messeging
FaceMessgpostiv143 | verify user able to send video from camera with backgraund in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on camera icon select your backgraund record a video , click send | [7 empty] | positive | messeging
FaceMessgpostiv144 | verify user able to send photo from camera with boomerang in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on camera icon select boomerang tacke a photo , click send | [7 empty] | positive | messeging
FaceMessgpostiv145 | verify user able to send photo from camera with selfie in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on camera icon select selfie tacke a photo , click send | [7 empty] | positive | messeging
FaceMessgnegativ146 | verify user able to send location in chat when device location turn on |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click in four duts ,click on location icon define your locatoin , send location | [7 empty] | Negativ | messeging
FaceMessgnegativ147 | verify user able to unsend messeg after his friend sow it |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him hold on messeg ,select more click unsend | [7 empty] | Negativ | messeging
FaceMessgnegativ148 | verify user able to select multi messege to remove it |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him hold on messeg ,select more than messege | [7 empty] | Negativ | messeging
FaceMessgnegativ149 | verify user able to send th same photo with multiple photos in two Consecutive messeges |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select multi photo from gallery , send select multi photo from gallery , send review sent photos | [7 empty] | Negativ | messeging
FaceMessgnegativ150 | verify user able to messeging from facebook with out instule messenger |  | open Facebook app ,login your account oppen your friend profile click on messenge button | [7 empty] | Negativ | messeging
FaceMessgnegativ151 | verify user able to send corrupted img |  | open Facebook app ,login your account click on messenge icon select your friend to oppen chat with him select your corrupted img send | [7 empty] | Negativ | messeging
FaceMessgnegativ152 | verify user able to switch between wifi and data during his media is loading |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select multi photo from gallery , send switch between wifi and data during photos loading | [7 empty] | Negativ | messeging
FaceMessgnegativ153 | verify user able to turn off wifi or data during his media is loading |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select multi photo from gallery , send turn off wifi or data during photos loading | [7 empty] | Negativ | messeging

## FR1 adding post
TC ID | TC Name | Precondition | Steps to be executed | testeData | ExpectedResult | ActualResult | priority | status | requierment traciabilty | bug traciabilty | test type | medeule name
FaceGUI01 | verefy user able to create new text poste from home | Facebook App is instaling and oppening | open Facebook app ,login your account click on what's on your mined? write your text , click post |  | new post is created | poste is created | high | pass | FR1 : add posts |  | GUI | adding post
FaceGUI02 | verefy user able to create new photo post from home by photo icon |  | open Facebook app ,login your account home page, click on photo icon select your photos from gallary,,Next ,POST |  | new photo post is created | new photo post is created | high | Pass | FR1 : add posts |  | GUI | adding post
FaceGUI03 | verefy user able to specifing who can see his post?friends |  | open Facebook app ,login your account home page, lick on what's on your mined? click on post audience, select frends |  | your audience is your friends | your audience is your friends | high | pass | FR1 : add posts |  | GUI | adding post
FaceGUI04 | verefy user able to add feeling to the post |  | open Facebook app ,login your account home page,click on what's on your mined? click on face icon ,select your feeling click done ,POST |  | add fealing | add fealing | low | pass | FR1 : add posts |  | GUI | adding post
FaceGUI05 | verify user able to tag people in the post |  | open Facebook app ,login your account home page, click on what's on your mined? click on tag people , post |  | tage people in the post | tage people in the post | medum | pass | FR1 : add posts |  | GUI | adding post
FaceGUI06 | verefy user able to add effect to the post photo |  | open Facebook app ,login your account home page , click on what's on your mined? click on photo icon , select your photos from gallary Next , add effect to the photo ,POST |  | effect is adding | effect is adding | medum | pass | FR1 : add posts |  | GUI | adding post
FaceGUI07 | verefy user able to add filter to the post photo |  | open Facebook app ,login your accoun home paget , click on what's on your mined? click on photo icon , select your photos from gallary Next , add filter to the photo ,Post |  | filter is adding | filter is adding | medum | pass | FR1 : add posts |  | GUI | adding post
FaceGUI08 | verefy user able to add effect to the post video |  | open Facebook app ,login your account home page , click on what's on your mined? click on photo icon , select your video from gallary Next , add effect to the photo ,Post |  | video is adding with effect | the app hanging | medum | fail | FR1 : add posts | Facebug#1 | GUI | adding post
FaceGUI09 | verefy user able to add video from gallary with photo from camera and text to the post |  | open Facebook app ,login your account home page , click on what's on your mined? write text , click on photo icon select your video from gallary, Next add photo from camera to the photo ,Post |  | photo with video and text is added | photo with video and text is added | medum | pass | FR1 : add posts |  | GUI | adding post
FaceGUI10 | verefy user able to add video from the camera |  | open Facebook app ,login your account home page , click on what's on your mined? select camera,select video,recored video,done , post |  | video is posted | video is posted | high | pass | FR1 : add posts |  | GUI | adding post
FaceGUI11 | verefy user able to add photo from the camera |  | open Facebook app ,login your account home page , click on what's on your mined? select camera , tack photo, done , post |  | photo is posted | photo is posted | high | pass | FR1 : add posts |  | GUI | adding post
FaceGUI12 | verefy user able to add gif |  | open Facebook app ,login your account home page , click on what's on your mined? click on gif icon ,select your gif , don ,post |  | gif is posted | gif is posted | medum | pass | FR1 : add posts |  | GUI | adding post
FaceGUI13 | verefy user able to add music |  | open Facebook app ,login your account home page , click on what's on your mined? click on music icon ,select your music , don ,post |  | music is posted | music is posted | medum | pass | FR1 : add posts |  | GUI | adding post
FaceGUI14 | verefy user able to add locasion |  | open Facebook app ,login your account , home page click on what's on your mined? click oncheck in icon ,allow app oppen location select location ,done , post |  | is posted |  |  |  | FR1 : add posts |  | GUI | adding post
FaceGUI15 | verefy user able to create new poste text with photo from gallary |  | open Facebook app ,login your account home page click on what's on your mined? write your text , click on photo icon select your photos,Next ,POST |  | post is added | post is added | high | pass | FR1 : add posts |  | GUI | adding post
FaceGUI16 | verefy user able to create new photo post from profile page by photo icon beside what's on your mined? |  | open Facebook app ,login your account profile page, click on photo icon select your photos from gallary,Next ,POST |  | new photo post is created | new photo post is created | high | Pass | FR1 : add posts |  | GUI | adding post
FaceGUI17 | verefy user able to create new text poste from profile page | Facebook App is instaling and oppening | open Facebook app ,login your account profile page click on what's on your mined? write your text , click post |  | new post is created | poste is created | high | pass | FR1 : add posts |  | GUI | adding post
FaceGUI18 | verefy user able to create new photo post from profile page by photo icon in what's on your mined? |  | open Facebook app ,login your account profile page,what's on your mined?, click on photo icon select your photos from gallary,,Next ,POST |  | new photo post is created | new photo post is created | high | Pass | FR1 : add posts |  | GUI | adding post
FaceGUI19 | verefy user able to specifing who can see his post? friends from profile page |  | open Facebook app ,login your account profile page, lick on what's on your mined? click on post audience, select friends |  | your audience is your friends | your audience is your friends | high | pass | FR1 : add posts |  | GUI | adding post
FaceGUI20 | verefy user able to add feeling to the post from profile page |  | open Facebook app ,login your account profile page,click on what's on your mined? click on face icon ,select your feeling click done ,POST |  | add fealing | add fealing | low | pass | FR1 : add posts |  | GUI | adding post
FaceGUI21 | verify user able to tag people in the post from profile page |  | open Facebook app ,login your account profile page, click on what's on your mined? click on tag people , post |  | tage people in the post | tage people in the post | medum | pass | FR1 : add posts |  | GUI | adding post
FaceGUI22 | verefy user able to add effect to the post photo from profile page |  | open Facebook app ,login your account profile page , click on what's on your mined? click on photo icon , select your photos from gallary Next , add effect to the photo ,POST |  | effect is adding | effect is adding | medum | pass | FR1 : add posts |  | GUI | adding post
FaceGUI23 | verefy user able to add filter to the post photo from profile page |  | open Facebook app ,login your accoun profile page , click on what's on your mined? click on photo icon , select your photos from gallary Next , add filter to the photo ,Post |  | filter is adding | filter is adding | medum | pass | FR1 : add posts |  | GUI | adding post
FaceGUI24 | verefy user able to add effect to the post video from profile page |  | open Facebook app ,login your account profile page , click on what's on your mined? click on photo icon , select your video from gallary Next , add effect to the photo ,Post |  | effect is adding | the app hanging | medum | fail | FR1 : add posts | Facebug#2 | GUI | adding post
FaceGUI25 | verefy user able to add video from gallary with photo from camera and text to the post from profile page |  | open Facebook app ,login your account profile page , click on what's on your mined? write text , click on photo icon select your video from gallary, Next add photo from camera to the photo ,Post |  | photo with video and text is added | photo with video and text is added | medum | pass | FR1 : add posts |  | GUI | adding post
FaceGUI26 | verefy user able to add video from the camera from profile page |  | open Facebook app ,login your account profile page , click on what's on your mined? select camera,select video,recored video,done , post |  | video is posted | video is posted | high | pass | FR1 : add posts |  | GUI | adding post
FaceGUI27 | verefy user able to add photo from the camera from profile page |  | open Facebook app ,login your account profile page , click on what's on your mined? select camera , tack photo, done , post |  | photo is posted | photo is posted | high | pass | FR1 : add posts |  | GUI | adding post
FaceGUI28 | verefy user able to add gif from profile page |  | open Facebook app ,login your account profile page , click on what's on your mined? click on gif icon ,select your gif , don ,post |  | gif is posted | gif is posted | medum | pass | FR1 : add posts |  | GUI | adding post
FaceGUI29 | verefy user able to add music from profile page |  | open Facebook app ,login your account profile page , click on what's on your mined? click on music icon ,select your music , don ,post |  | music is posted | music is posted | medum | pass | FR1 : add posts |  | GUI | adding post
FaceGUI30 | verefy user able to add locasion from profile page |  | open Facebook app ,login your account , profile page click on what's on your mined? click oncheck in icon ,allow app oppen location select location ,done , post |  | is posted |  |  |  | FR1 : add posts |  | GUI | adding post
FaceGUI31 | verefy user able to create new post text with photo from gallary from profile page |  | open Facebook app ,login your account from profile page click on what's on your mined? write your text , click on photo icon select your photos,Next ,POST |  | post is added | post is added | high | pass | FR1 : add posts |  | GUI | adding post
FaceGUI32 | verefy user able to create new post live from home and profile page |  | open Facebook app ,login your account from home page or profile page click on what's on your mined? click on live icon start live,finish ,Post to profile |  | live is added | live is added | medum | pass | FR1 : add posts |  | GUI | adding post
FaceGUI33 | verify filters worke sucsisfuly |  | open Facebook app ,login your account from profile page click on filters select your filter,Done |  | only veiw related postes | only veiw related postes | medum | pass | FR1 : add posts |  | GUI | adding post
FaceGUI34 | verify live icon under what's on your mined? worke sucsisfuly |  | open Facebook app ,login your account from profile page click on live icon start live,finish ,Post to profil |  | live is added | live is added | medum | pass | FR1 : add posts |  | GUI | adding post
Facepossetiv35 | verefy user able to delet post |  | open Facebook app ,login your account from profile page click on manage posts select post , click on junk icon Delet posts,DELETPOSTS in message |  | post is deleting | post is deleting | high | pass | FR1 : add posts |  | Positive | adding post
Facepossetiv36 | verefy user able to Remove tags from posts |  | open Facebook app ,login your account from profile page click on manage posts select tags post , click on tags icon Remove tags |  | tage is Remove | tage tag icon unactive | high | fail | FR1 : add posts |  | Positive | adding post
Facepossetiv37 | verefy user able to finish his post later |  | open Facebook app ,login your account profile page or home page click on what's on your mined? write your text , click bake select save as draft | [5 empty] | FR1 : add posts |  | Positive | adding post
Facepossetiv38 | verefy user able to Discard post his post later |  | open Facebook app ,login your account profile page or home page click on what's on your mined? write your text , click bake Discard post | [5 empty] | FR1 : add posts |  | Positive | adding post
Facepossetiv39 | verefy user able to specifing his post audience |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on audience butne ,select your audience | [5 empty] | FR1 : add posts |  | Positive | adding post
Facepossetiv40 | verefy user able to creat new album |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on album ,creat new albom | [5 empty] | FR1 : add posts |  | Positive | adding post
Facepossetiv41 | verefy user able to add posts to album |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on album,select your album | [5 empty] | FR1 : add posts |  | Positive | adding post
Facepossetiv42 | verefy user able to share his post photo to Instagram |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on Instagram icon turn on Instagram | [5 empty] | FR1 : add posts |  | Positive | adding post
Facenegativ43 | verefy user able to share his text post to Instagram |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Write your post Click on Instagram icon turn on Instagram | [5 empty] | FR1 : add posts |  | Negativ | adding post
Facenegativ44 | verefy user able to share his audues post to Instagram |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on music Select your audue Click on Instagram icon turn on Instagram | [5 empty] | FR1 : add posts |  | Negativ | adding post
Facenegativ45 | verefy user able to share his audues post to Instagram |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on chick in Select your location Click on Instagram icon turn on Instagram | [5 empty] | FR1 : add posts |  | Negativ | adding post
Facenegativ46 | verefy user able to share his fealing only in post to Instagram |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on feeling Select your fealing Click on Instagram icon turn on Instagram | [5 empty] | FR1 : add posts |  | Negativ | adding post
Facenegativ47 | verefy user able to share background color post to Instagram |  | open Facebook app ,login your account profile page or home page click on what's on your mined? Click on background color Select your background color Click on Instagram icon turn on Instagram | [5 empty] | FR1 : add posts |  | Negativ | adding post
Facenegativ48 | verefy user able to add photo with text extention | [7 empty] | FR1 : add posts |  | Negativ | adding post
Facenegativ49 | verefy user able to add video with text extention | [7 empty] | FR1 : add posts |  | Negativ | adding post
Facenegativ50 | verefy user able to add video violent content | [7 empty] | FR1 : add posts |  | Negativ | adding post

## FR2 adding Story
TC ID | TC Name | Precondition | Steps to be executed | testeData | ExpectedResult | ActualResult | priority | status | requierment traciabilty | bug traciabilty | test type | medeule name
FaceStoryGUI51 | verefy user able to add text story |  | open Facebook app ,login your account profile page click add to story or home page creat story select text , write your text Done ,share |  | New story text is adding | new story text is adding | high | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI52 | verefy user able to add music story |  | open Facebook app ,login your account profile page click add to story or home page creat story click music , select music Done ,share |  | New music story is adding | New music story is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI53 | verefy user able to add green screen photo story |  | open Facebook app ,login your account profile page click add to story click green screen , select scenes tacke a photo ,Done ,share |  | New story with green screen photo is adding | New story with green screen photo is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI54 | verefy user able to add green screen photo with music story |  | open Facebook app ,login your account profile page click add to story click green screen , select scenes tacke a photo , select your music ,Done ,share |  | New story with green screen photo and music is adding | New story with green screen photo and music is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI55 | verefy user able to add multi story |  | open Facebook app ,login your account profile page click add to story select text , write your text Done ,share click add to story click music , select music Done ,share |  | New story with text and music is adding | New story with text and music is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI56 | verefy user able to add BOOMERANG photo story |  | open Facebook app ,login your account profile page click add to story click BOOMERANG tacke a photo ,Done ,share |  | New story with Boomerang photo is adding | New story with Boomerang photo is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI57 | verefy user able to add Boomerang photo with music story |  | open Facebook app ,login your account profile page click add to story click BOOMERANG tacke a photo , select your music ,Done ,share |  | New story with Boomerang photo and music is adding | New story with Boomerang photo and music is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI58 | verefy user able to add selfie photo story |  | open Facebook app ,login your account profile page click add to story click selfie tacke a photo ,share |  | New story with selfie photo is adding | New story with selfie photo is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI59 | verefy user able to add selfie photo with music story |  | open Facebook app ,login your account profile page click add to story click selfie tacke a photo , select your music ,share |  | New story with selfie photo and music is adding | New story with selfie photo and music is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI60 | verefy user able to add effect to music story |  | open Facebook app ,login your account profile page click add to story click music , select music add effect ,Done ,share |  | New music story with effect is adding | New music story with effect is adding | low | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI61 | verefy user able to add effect to green screen photo story |  | open Facebook app ,login your account profile page click add to story click green screen , select scenes tacke a photo , add effect ,Done ,share |  | New story with green screen photo and effect is adding | New story with green screen photo and effect is adding | low | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI62 | verefy user able to add effect to Boomerang photo story |  | open Facebook app ,login your account profile page click add to story click BOOMERANG tacke a photo , select effect ,Done ,share |  | New story with Boomerang photo and effect is adding | New story with Boomerang photo and effect is adding | low | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI63 | verefy user able to add effect to selfie photo story |  | open Facebook app ,login your account profile page click add to story click selfie , select effect tacke a photo ,share |  | New story with selfie photo and effect is adding | New story with selfie photo and effect is adding | low | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI64 | verefy user able to add green screen video with music story |  | open Facebook app ,login your account profile page click add to story click green screen , select scenes hold to record a video , select your music Done ,share |  | New story with green screen video is adding | New story with green screen video is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI65 | verefy user able to add Boomerang video with music story |  | open Facebook app ,login your account profile page click add to story select Boomerang hold on BOOMERANG record a video select your music ,Done ,share |  | New story with Boomerang video is adding | New story with Boomerang video is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI66 | verefy user able to add selfie video with music story |  | open Facebook app ,login your account profile page click add to story click selfie record a video , select sound , add music select your music ,share |  | New story with silfie video is adding | New story with selfie video is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI67 | verefy user able to add effect to green screen video story |  | open Facebook app ,login your account profile page click add to story click green screen , select scenes hold to record a video , click on effects select effect ,Done ,share |  | New story with green screen video and effect is adding | New story with green screen video and effect is adding | low | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI68 | verefy user able to add effect to Boomerang video story |  | open Facebook app ,login your account profile page click add to story click BOOMERANG hold to record a video , click on effects select effect ,Done ,share |  | New story with Boomerang video and effect is adding | New story with Boomerang video and effect is adding | low | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI69 | verefy user able to add effect to selfie video story |  | open Facebook app ,login your account profile page click add to story click selfie ,hold to record a video click on effects select effect,share |  | New story with silfie video and effect is adding | New story with silfie video and effect is adding | low | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI70 | verefy user able to add a photo from camera to story |  | open Facebook app ,login your account profile page click add to story click camera icon ,tacke a photo , share |  | New story with camera photo is adding | New story with camera photo is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI71 | verefy user able to add a photo from camera with music and effect to story |  | open Facebook app ,login your account profile page click add to story click camera icon ,select your effect tacke a photo select your music , share |  | New story with camera photo and effects is adding | New story with camera photo and effects is adding | low | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI72 | verefy user able to add a video from camera to story |  | open Facebook app ,login your account profile page click add to story click camera icon ,select video record the video, share |  | New story with camera video is adding | New story with camera video is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI73 | verefy user able to add a video from camera with music and effect to story |  | open Facebook app ,login your account profile page click add to story click camera icon ,select video record the video , click on effects select your effect select your music , share |  | New story with camera video , music and effects is adding | New story with camera video ,music and effects is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI74 | verefy user able to add a photo from gallery to story |  | open Facebook app ,login your account profile page click add to story select photo from gallery , share |  | New story with gallery photo is adding | New story with gallery photo is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI75 | verefy user able to add effects to the photo from gallery to story |  | open Facebook app ,login your account profile page click add to story select photo from gallery , click on effects select your effect , share |  | New story with gallery photo and effects is adding | New story with gallery photo and effects is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStoryGUI76 | verefy user able to add a photo from gallery with music to story |  | open Facebook app ,login your account profile page click add to story select photo from gallery , select music , share |  | New story with gallery photo and music is adding | New story with gallery photo and music is adding | medum | pass | FR2: add story |  | GUI | adding story
FaceStorypost77 | verefy user able to add a video from gallery to story |  | open Facebook app ,login your account profile page click add to story select video from gallery , share |  | New story with gallery video is adding | New story with gallery video is adding | medum | pass | FR2: add story |  | Positive | adding story
FaceStorypost78 | verefy user able to add effects to the video from gallery to story |  | open Facebook app ,login your account profile page click add to story select video from gallery , click on effects select your effect , share |  | New story with gallery video and effects is adding | New story with gallery video and effects is adding | low | pass | FR2: add story |  | Positive | adding story
FaceStorypost79 | verefy user able to add a video from gallery with music to story |  | open Facebook app ,login your account profile page click add to story select video from gallery , select music , share |  | New story with gallery video and music is added | New story with gallery video and music is added | medum | pass | FR2: add story |  | Positive | adding story
FaceStorypost80 | verefy user able to always share green screen photo with music story to instagram |  | open Facebook app ,login your account profile page click add to story click green screen , select scenes click to tacke photo , select your music click on privacy ,Always share to instagram turn on ,share |  | New story with green screen photo and music is shared to facebook story and instagram | New story with green screen photo and music is shared to facebook story and instagram | medum | pass | FR2: add story |  | Positive | adding story
FaceStorypost81 | verefy user able to always share Boomerang photo with music story to instagram |  | open Facebook app ,login your account profile page click add to story select Boomerang,click Boomerang , click to tacke photo , select your music click on privacy ,Always share to instagram turn on ,share |  | New story Boomerang photo with music is shared to facebook story and instagram | New story Boomerang photo with music is shared to facebook story and instagram | medum | pass | FR2: add story |  | Positive | adding story
FaceStorypost82 | verefy user able to always share selfie photo with music story to instagram |  | open Facebook app ,login your account profile page click add to story click selfie click to tacke photo , select your music click on privacy ,Always share to instagram turn on ,share |  | New story selfie photo with music is shared to facebook story and instagram | New story selfie photo video with music is shared to facebook story and instagram | medum | pass | FR2: add story |  | Positive | adding story
FaceStorypost83 | verefy user able to always share a photo from gallery with music story to instagram |  | open Facebook app ,login your account profile page click add to story select photo from gallery , select music click on privacy ,Always share to instagram turn on , share |  | New story gallery photo with music is shared to facebook story and instagram | New story gallery photo with music is shared to facebook story and instagram | medum | pass | FR2: add story |  | Positive | adding story
FaceStorypost84 | verefy user able to always share a photo from camera with music story to instagram |  | open Facebook app ,login your account profile page click add to story click camera icon ,tacke a photo, select music click on privacy ,Always share to instagram turn on , share |  | New story camera photo with music is shared to facebook story and instagram | New story camera photo with music is shared to facebook story and instagram | medum | pass | FR2: add story |  | Positive | adding story
FaceStorypost85 | verefy user able to always share a video from gallery with music story to instagram |  | open Facebook app ,login your account profile page click add to story select video from gallery , select music click on privacy ,Always share to instagram turn on , share |  | New story gallery video with music is shared to facebook story and instagram | New story gallery video with music is shared to facebook story and instagram | medum | pass | FR2: add story |  | Positive | adding story
FaceStorypost86 | verefy user able to always share a video from camera with music story to instagram |  | open Facebook app ,login your account profile page click add to story click camera icon ,select video record the video, select music click on privacy ,Always share to instagram turn on , share |  | New story camera video with music is shared to facebook story and instagram | New story camera video with music is shared to facebook story and instagram | medum | pass | FR2: add story |  | Positive | adding story
FaceStorypost87 | verefy user able to always share green screen video with music story to instagram |  | open Facebook app ,login your account profile page click add to story click green screen , select scenes hold to record a video , select your music click on privacy ,Always share to instagram turn on ,share |  | New story green screen video with music is shared to facebook story and instagram | New story green screen video with music is shared to facebook story and instagram | medum | pass | FR2: add story |  | Positive | adding story
FaceStorypost88 | verefy user able to always share Boomerang photo with music story to instagram |  | open Facebook app ,login your account profile page click add to story select Boomerang,click Boomerang , hold to record a video , select your music click on privacy ,Always share to instagram turn on ,share |  | New story Boomerang video with music is shared to facebook story and instagram | New story Boomerang video with music is shared to facebook story and instagram | medum | pass | FR2: add story |  | Positive | adding story
FaceStorypost89 | verefy user able to always share selfie photo with music story to instagram |  | open Facebook app ,login your account profile page click add to story click selfie hold to record a video , select your music click on privacy ,Always share to instagram turn on ,share |  | New story selfie video with music is shared to facebook story and instagram | New story selfie video with music is shared to facebook story and instagram | medum | pass | FR2: add story |  | Positive | adding story
FaceStorypost90 | verefy user able to select multiple photo from gallery |  | open Facebook app ,login your account profile page or home creat story click add to story click select multiple ,select your photos click Next,click share. | [5 empty] | FR2: add story |  | Positive | adding story
FaceStorypost91 | verefy user able to select multiple photo from gallery and add music to every photo |  | open Facebook app ,login your account profile page or home creat story click add to story click select multiple ,select your photos edit every photo ,select music to every photo click Next,click share. | [5 empty] | FR2: add story |  | Positive | adding story
FaceStorypost92 | verefy user able to select multiple video from gallery |  | open Facebook app ,login your account profile page or home creat story click add to story click select multiple ,select your videos click Next,click share. | [5 empty] | FR2: add story |  | Positive | adding story
FaceStorypost93 | verefy user able to select multiple videos from gallery and add music to every video |  | open Facebook app ,login your account profile page or home creat story click add to story click select multiple ,select your videos edit every video ,select music to every video click Next,click share. | [5 empty] | FR2: add story |  | Positive | adding story
FaceStorypost94 | verefy user able to select multiple photo from gallery and add effects to them |  | open Facebook app ,login your account profile page or home creat story click add to story click select multiple ,select your photos edit every photo , click effects select effect to every photo click Done , click share. | [5 empty] | FR2: add story |  | Positive | adding story
FaceStorypost95 | verefy user able to select multiple video from gallery and add effects to them |  | open Facebook app ,login your account profile page or home creat story click add to story click select multiple ,select your videos edit every video , click effects select effect to every video click Done , click share. | [5 empty] | FR2: add story |  | Positive | adding story
FaceStorypost96 | verefy user able to select multiple videos and photos from gallery and add stickers to them |  | open Facebook app ,login your account profile page or home creat story click add to story click select multiple ,select your videos and photos ,edit every video and photo click stickers ,select stickers to every video and photo click Done , click share. | [5 empty] | FR2: add story |  | Positive | adding story
FaceStorynegat97 | verefy user able to always share music story to instagram |  | open Facebook app ,login your account profile page click add to story click music , select your music click on privacy ,Always share to instagram turn on ,share | [5 empty] | FR2: add story |  | Positive | adding story
FaceStorynegat98 | verefy user able to always share text story to instagram |  | open Facebook app ,login your account profile page click add to story click text , write your text click on privacy ,Always share to instagram turn on ,share | [5 empty] | FR2: add story |  | Negativ | adding story
FaceStorynegat99 | verefy user able to edit his story privacy public when he locked his profile |  | open Facebook app ,login your account profile page click add to story , add your photo or video or any type of storeis by any way click on privacy,select public | [5 empty] | FR2: add story |  | Negativ | adding story
FaceStorynegat100 | verify user story is visible after 24 hour on face book and messenger |  | open Facebook app ,login your account veiw your story or click on messenger icon to go to messenger , veiw your story after 25 hour | [5 empty] | FR2: add story |  | Negativ | adding story
FaceStorynegat101 | verify user able to custom friend and hide the same story from the same friend |  | open Facebook app ,login your account profile page click add to story , add your photo or video or any type of storeis by any way click on privacy,select custom select singl friend ,click hid story from the same singl friend | [5 empty] | FR2: add story |  | Negativ | adding story
FaceStorynegat102 | verify friend able to see your story you are hide this story from this friend |  | open Facebook app ,login your anather account oppen stories are you see the story | [5 empty] | FR2: add story |  | Negativ | adding story
FaceStorynegat103 | verify friend able to comment in your story you are turn comments off for this story |  | open Facebook app ,login your anather account oppen stories try to comment in the story | [5 empty] | FR2: add story |  | Negativ | adding story

## FR3 messeging
TC ID | TC Name | Precondition | Steps to be executed | testeData | ExpectedResult | ActualResult | priority | status | requierment traciabilty | bug traciabilty | test type | medeule name
FaceMessgGUI104 | verify user able to oppen chating with any friend |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him |  | chat is oppened | chat is oppened | high | pass | FR3 : Messaging |  | GUI | messeging
FaceMessgGUI105 | verify user able to send text messege in chat to his friend friend |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him write your text messege , click send |  | messege is sent | messege is sent | high | pass | FR3 : Messaging |  | GUI | messeging
FaceMessgGUI106 | verify user able to send a messege by pen icon to singel friend |  | open Facebook app ,login your account click on messenger icon click on pen icon select your single friend write your messege , click send |  | messege is sent | messege is sent | high | pass | FR3 : Messaging |  | GUI | messeging
FaceMessgGUI107 | verify user able to by send messege by pen icon to multi friend |  | open Facebook app ,login your account click on messenger icon click on pen icon select your multi friend write your messege , click send |  | messege is sent to every friend in his praivte chat | messege is sent in new grope | high | fail | FR3 : Messaging | Facebug#3 | GUI | messeging
FaceMessgGUI108 | verify user able to see his new notification from chats icon when it will be blue |  | open Facebook app ,login your account click on messenger icon click on chats icon |  | user notfication is oppend | user notfication is oppend | high | pass | FR3 : Messaging |  | GUI | messeging
FaceMessgGUI109 | verify user able to search about any one on facebook to chat with this person |  | open Facebook app ,login your account click on messenger icon in search tabe write name click search , select name start chating |  | veiw related result | veiw related result | medum | pass | FR3 : Messaging |  | GUI | messeging
FaceMessgGUI110 | verify user able to search about any friend in facebook to chat with this friend |  | open Facebook app ,login your account click on messenger icon in search tabe write your friend name click search , select your friend start chating |  | veiw related result | veiw related result | high | pass | FR3 : Messaging |  | GUI | messeging
FaceMessgGUI111 | verify user able to connect by video call with any single friend in facebook by start call icon |  | open Facebook app ,login your account click on messenger icon click start call icon select friend , click start call button |  | call is started | call is started | high | pass | FR3 : Messaging |  | GUI | messeging
FaceMessgGUI112 | verify user able to connect by video call with multibl friend in facebook by start call icon |  | open Facebook app ,login your account click on messenger icon click start call icon select 2 friends or more , click start call button |  | call is started | call is started | high | pass | FR3 : Messaging |  | GUI | messeging
FaceMessgGUI113 | verify user able to send a photo from gallery in messege in chat to friend |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo , click send |  | photo Message delivered | photo Message delivered | high | pass | FR3 : Messaging |  | GUI | messeging
FaceMessgGUI114 | verify user able to send a photo from camera in messege in chat to friend |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on camera icon , tacke photo, click send |  | takes a picture with the camera and it sent | takes a picture with the camera and it sent | high | pass | FR3 : Messaging |  | GUI | messeging
FaceMessgGUI115 | verify user able to send a voice note in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him holde on microphon icon ,say what you want , Lift your finger |  | voice note is sent | voice note is sent | high | pass | FR3 : Messaging |  | GUI | messeging
FaceMessgGUI116 | verify user able to send a like expretion in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click in like icon |  | like simpole is sent | like simpole is sent | low | pass | FR3 : Messaging |  | GUI | messeging
FaceMessgGUI117 | verify user able to send location in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click in four duts ,click on location icon define your locatoin , send location |  | right location is sent | right location is sent | high | pass | FR3 : Messaging |  | GUI | messeging
FaceMessgGUI118 | verify user able to send a voice note from chat to anther chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on share icon ,beside the voice note , click send beside any friend you need |  | voice note is sent to your selected friends | voice note is sent to your selected friends | medum | pass | FR3 : Messaging |  | GUI | messeging
FaceMessgpostiv119 | verify user able to send an emojy in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him in writing tabe click on emojy select your emojy , send |  | emojy is sent | emojy is sent | medum | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv120 | verify user able to send a gif in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him in writing tabe click on emojy ,click gif icon select your gif |  | gif is sent | gif is sent | low | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv121 | verify user able to send sounds in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him in writing tabe click on emojy ,click sound icon select your sound , send |  | sound is sent | sound is sent | low | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv122 | verify user able to send stickers in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him in writing tabe click on emojy ,click stickers icon select and click on your sticker |  | sticker is sent | sticker is sent | low | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv123 | verify user able to send star stickers in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him in writing tabe click on emojy ,click star icon select and click on your sticker |  | sticker is sent | sticker is sent | low | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv124 | verify user able to send video from gallery in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your video , ,click send |  | video is sent | video is sent | high | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv125 | verify user able to send video from gallery with sticker in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your video, click edit select sticker , done , click send |  | video is sent with sticker | video is sent with sticker | medum | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv126 | verify user able to send multi video from gallery in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your videos , ,click send |  | videos is sent | videos is sent | medum | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv127 | verify user able to send video from gallery with cut it in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your video, click edit click cut icon , cut video , click send |  | cuting video is sent | cuting video is sent | high | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv128 | verify user able to send video from gallery with text in video in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your video, click edit click text icon , write text in video done , click send |  | video with text is sent | video with text is sent | medum | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv129 | verify user able to send video from gallery with a drawing in video in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your video, click edit click brush icon , draw in video done , click send |  | video with adrawing is sent | video with adrawing is sent | medum | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv130 | verify user able to send photo from gallery with sticker in in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo, click edit select sticker , done , click send |  | photo is sent with sticker | photo is sent with sticker | low | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv131 | verify user able to send multi photo from gallery in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photos , ,click send |  | photos is sent | photos is sent | medum | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv132 | verify user able to send photo from gallery with cropt it in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo , click edit click cropt icon , cropt photo done , click send |  | cropted photo is sent | cropted photo is sent | high | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv133 | verify user able to send photo from gallery with text in photo in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo click edit click text icon ,select text aligne or text backgraund write text in photo done , click send |  | photo with text is sent | photo with text is sent | medum | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv134 | verify user able to send photo from gallery with a drawing in photo in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo click edit click brush icon , draw in photo done , click send |  | photo with adrawing is sent | photo with adrawing is sent | medum | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv135 | verify user able to send photo from gallery with an effect photo in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo click edit click effects icon , select your effect done , click send |  | photo with effect is sent | photo with effect is sent | low | pass | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv136 | verify user able to send photo from gallery with a filter photo in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo click edit click filters icon , select your filter done , click send | [5 empty] | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv137 | verify user able to send photo from gallery with a coloradjustment photo in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select your photo click edit click coloradjustment icon , select your coloradjustment done , click send | [5 empty] | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv138 | verify user able to send photo from camera by camera icon beside the sent photos in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on cameraicon beside the sent photos in chat , tacke a photo click send | [5 empty] | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv139 | verify user able to send photo from camera by camera icon beside the sent photos in chat with sticker |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on cameraicon beside the sent photos in chat , tacke a photo click edit , select sticker done , click send | [5 empty] | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv140 | verify user able to send photo from camera by camera icon beside the sent photos in chat with effect |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on camera icon beside the sent photos in chat , tacke a photo click edit , select effect done , click send | [5 empty] | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv141 | verify user able to send text photo from camera in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on camera icon , select text photo write a text , click send | [5 empty] | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv142 | verify user able to send video from camera in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on camera icon , record a video click send | [5 empty] | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv143 | verify user able to send video from camera with backgraund in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on camera icon select your backgraund record a video , click send | [5 empty] | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv144 | verify user able to send photo from camera with boomerang in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on camera icon select boomerang tacke a photo , click send | [5 empty] | FR3 : Messaging |  | positive | messeging
FaceMessgpostiv145 | verify user able to send photo from camera with selfie in chat |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click on camera icon select selfie tacke a photo , click send | [5 empty] | FR3 : Messaging |  | positive | messeging
FaceMessgnegativ146 | verify user able to send location in chat when device location turn on |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him click in four duts ,click on location icon define your locatoin , send location | [5 empty] | FR3 : Messaging |  | Negativ | messeging
FaceMessgnegativ147 | verify user able to unsend messeg after his friend sow it |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him hold on messeg ,select more click unsend | [5 empty] | FR3 : Messaging |  | Negativ | messeging
FaceMessgnegativ148 | verify user able to select multi messege to remove it |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him hold on messeg ,select more than messege | [5 empty] | FR3 : Messaging |  | Negativ | messeging
FaceMessgnegativ149 | verify user able to send th same photo with multiple photos in two Consecutive messeges |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select multi photo from gallery , send select multi photo from gallery , send review sent photos | [5 empty] | FR3 : Messaging |  | Negativ | messeging
FaceMessgnegativ150 | verify user able to messeging from facebook with out instule messenger |  | open Facebook app ,login your account oppen your friend profile click on messenge button | [5 empty] | FR3 : Messaging |  | Negativ | messeging
FaceMessgnegativ151 | verify user able to send corrupted img |  | open Facebook app ,login your account click on messenge icon select your friend to oppen chat with him select your corrupted img send | [5 empty] | FR3 : Messaging |  | Negativ | messeging
FaceMessgnegativ152 | verify user able to switch between wifi and data during his media is loading |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select multi photo from gallery , send switch between wifi and data during photos loading | [5 empty] | FR3 : Messaging |  | Negativ | messeging
FaceMessgnegativ153 | verify user able to turn off wifi or data during his media is loading |  | open Facebook app ,login your account click on messenger icon select your friend to oppen chat with him select multi photo from gallery , send turn off wifi or data during photos loading | [5 empty] | FR3 : Messaging |  | Negativ | messeging

## issues
Bug ID | Module Name | Title | Environment | Steps to reproduce | Expected Results | Actual Results | Bug Type | Priority | Severity | Screenshot / Video | Status | Requirement Traceability | Test Case
Facebug#1 | adding post | verefy user unable to add effect to the post video | Infinix HOT 9 Play | open Facebook app ,login your account home page , click on what's on your mined? click on photo icon , select your video from gallary Next , add effect to the photo ,Post | video is adding with effect | the app hanging | functional | low | medum |  | new | FR1 : add posts | FaceGUI08
Facebug#2 | adding post | user unable to Remove tags from posts | Infinix HOT 9 Play | open Facebook app ,login your account from profile page click on manage posts select tags post , click on tags icon Remove tags | tage is Remove | tage tag icon unactive | functional | high | high |  | new | FR1 : add posts | Facepossetiv36
Facebug#3 | messeging | user unable to by send messege by pen icon to multi friend | Infinix HOT 9 Play | open Facebook app ,login your account click on messenger icon click on pen icon select your multi friend write your messege , click send | messege is sent to every friend in his praivte chat | messege is sent in new grope | functional | medum | medum |  |  | FR3 : messeging | FaceMessgGUI107